## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set up Spring Boot project with MySQL Database | MUST | None | Dhruv Jamwal | Completed
S1 | S1 | US-002 | Configure DB connection and create transactions table using JPA | MUST | US-001 | Dhruv Jamwal | Completed
S2 | S2 | US-003 | Accept transactions via REST API | MUST | US-002 | Dhruv Jamwal | Completed
S2 | S2 | US-004 | Create Transaction entity and repository | MUST | US-003 | Dhruv Jamwal | Completed
S3 | S3 | US-005 | Develop Transaction generator | SHOULD | US-004 | Dhruv Jamwal | Completed
S3 | S3 | US-006 | Generate normal and fraudulent transactions | SHOULD | US-005 | Dhruv Jamwal | Completed
S4 | S4 | US-007 | Rule engine for fraud detection | MUST | US-006 | Dhruv Jamwal | Completed
S4 | S4 | US-008 | Implement fraud detection rules | MUST | US-007 | Dhruv Jamwal | Completed
S5 | S5 | US-009 | Generate and store fraud alerts | MUST | US-008 | Dhruv Jamwal | Completed
S5 | S5 | US-010 | Risk score Analysis | MUST | US-009 | Dhruv Jamwal | Completed
S6 | S6 | US-011 | APIs to view and filter alerts | MUST | US-010 | Dhruv Jamwal | Completed
S6 | S6 | US-012 | Filter alerts by risk and rule type | MUST | US-011 | Dhruv Jamwal | Completed
S7 | S7 | US-013 | Dashboard to visualize fraud alerts | MUST | US-012 | Dhruv Jamwal | Completed
S7 | S7 | US-014 | Configured Dashboard KPIs to track Total Volume, Fraud Blocks, and API Latency (SLA) in real-time | MUST | US-013 | Dhruv Jamwal | Completed
S8 | S8 | US-015 | Create fraud scenarios and E-Mail alerts | MUST | US-008 | Dhruv Jamwal | Completed
S8 | S8 | US-016 | Evaluation metrics for system effectiveness | SHOULD | US-015 | Dhruv Jamwal | Completed
S9 | S9 | US-017 | ML-based fraud prediction | MUST | US-016 | Dhruv Jamwal | Completed
S9 | S9 | US-018 | Final demo and presentation | MUST | US-014 | Dhruv Jamwal | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7